## README
RevisionGrade System Ledger — Control Cockpit
LAST_LEDGER_REFRESH | 2026-04-28 | SYSTEM_STATE | U1 ENFORCED / BOUNDARY SHAPE RESOLVED / U2-003 + U2-006 IMPLEMENTED + PUSHED + LOCAL TEST-PROVEN / LIVE_PROOF_PENDING | Updated 2026-04-28
ACTIVE_BLOCKER | Run U2 live server/API-path proof; capture confidence_label, confidence_reasons, propagation_summary, NO_TEXTUAL_ANCHOR/reason_codes when applicable, and progress.gate_enforcement. | ACTIVE_EXECUTION_BLOCK | U2_FIDELITY_ENFORCEMENT = close 6 RCAs; U2-003/U2-006 are PARTIAL REMOTE IMPLEMENTATION, not RESOLVED
RCA_SYSTEM_STATUS | Batch 1 + Batch 2 applied; boundary RCA resolved; U2 entry RCAs implemented/pushed/test-proven locally but awaiting live proof. | NEXT_BATCH | Next: live U2 closure proof; do not use Phase 2E/RLS evidence to close U2.
RULE | RCA becomes the source of truth; roadmap tabs become views of RCA.
FINAL_PATCH | PV115 is a verification artifact, not an RCA. Boundary validation calibration uncertainty is now RESOLVED by raw PASS shape proof.
BOUNDARY_RCA | RCA-BOUNDARY-SHAPE-001 | STATUS | RESOLVED
PV115_ARTIFACT | PV115-GOLDEN-FIXTURE | STATUS | NOT_READY
RULE | No truth exists outside RCA rows or explicit verification artifacts.
NEXT_EXECUTION | Boundary shape closed; ROADMAP.md updated through ca12ade4; U2 commit 8ecdde70 pushed. Next: prove U2 behavior on live server/API path before resolving RCAs.
MICRO_PATCH | PROMOTION_RULE added to VERIFICATION_ARTIFACTS; ambiguity lifecycle normalized as AMBIGUOUS → RESOLVED. | STATUS | APPLIED | 2026-04-27

## Roadmap_System
RevisionGrade Roadmap System — Current Accurate Version
System status
SYSTEM_STATUS: EXECUTION_STABLE
FAILURE_VISIBILITY: HIGH
TRUTH_ENFORCEMENT: IN_PROGRESS
PRIMARY_BLOCKER: U2_PROPAGATION_ENFORCEMENT
SECONDARY_BLOCKER: PASS_1_OUTPUT_FEASIBILITY
ACTIVE_LLR_TRACK: LLR-004 CLASSIFICATION / CALIBRATION
Completed / Enforced
BLOCK_B_ATOMICITY — ENFORCED
PR #241: persist_evaluation_v2_atomic RPC added
PR #242: V2 persistence success path switched to atomic RPC
PR #243: RPC ambiguity hotfix merged
DB migration applied
service_role EXECUTE verified
Production success-path empirically proven:
job 29089ed6-0fc7-485b-a699-56498b950295
artifact af699bd8-1618-4971-a097-b4345f3e7733
Status:
ENFORCED
RELIABILITY_GATE — ENFORCED
100k soak passed
0 unclassified failures
0 wrong-location edits
0 lost writes
0 non-canonical statuses
0 silent fallbacks
Status:
ENFORCED
DIALOGUE_ATTRIBUTION_GATE_V2 — ENFORCED at gate level
Gate-level fix validated.
No current evidence that QG_DIALOGUE_ATTRIBUTION_UNDERAUDITED remains the active blocker on reachable post-fix runs.
Status:
ENFORCED, with continued monitoring
PHASE_1_OBSERVABILITY — STRUCTURAL ENFORCED / EMPIRICAL PARTIAL
Failure envelopes now exist on current paths.
Older jobs correctly show null envelopes.
Some PASS1 / LLR paths still need empirical proof and/or final catch-site hardening.
Status:
STRUCTURAL_ENFORCED
EMPIRICAL_PARTIAL
Open / Active
U2_PROPAGATION_ENFORCEMENT — PRIMARY BLOCKER
Problem:
The system detects uncertainty but does not yet enforce consequences.
Weak evidence can still coexist with confident summary/authority.
Required RCA Batch 2:
RCA-U2-001: Score / confidence mismatch
RCA-U2-002: Summary washing
RCA-U2-003: UI authority overstatement
RCA-U2-004: Confidence not deterministically derived
RCA-U2-005: Missing propagation aggregation
Files:
qualityGate.ts
runPipeline.ts
runPass3Synthesis.ts
persistEvaluationResultV2.ts
warningClassification.ts
evaluation-result-v2.ts
confidenceDerivation.ts
tests / PV115 golden fixture
Status:
NOT_STARTED / NEXT ACTIVE EXECUTION BLOCK
PASS_1_OUTPUT_FEASIBILITY — SECONDARY BLOCKER
Problem:
Pass 1 frequently exceeds output capacity:
finish_reason=length
completion_tokens=3500
empty response
PASS1_FAILED
Correct framing:
PASS1 is not the main truth-enforcement priority.
PASS1 is the reachability blocker that prevents U2 from being empirically exercised.
Minimal fix only:
Reduce Pass 1 output surface
Limit evidence anchors to 1
Remove recommendations from Pass 1
Remove deep rationale from Pass 1
Keep fail-closed behavior
Status:
OPEN / PARALLEL MINIMAL FIX
LLR-004 / LLR_POST_DIAGNOSTIC_BLOCK — OPEN CLASSIFICATION TRACK
Meaning:
Pass 2 diagnostic output is being blocked by Lessons Learned enforcement.
This is upstream of U2 and unrelated to dialogue gate.
Possible causes:
MODEL_VIOLATION
RULE_OVERSTRICT
REGISTRY_DRIFT
AMBIGUOUS
Workbook change required:
Add rule_strictness_flag
Add enforcement_vs_calibration
Set RCA-LLR-004-001:
rule_strictness_flag = AMBIGUOUS
enforcement_vs_calibration = UNKNOWN
Status:
OPEN / NEEDS INCIDENT CLASSIFICATION
Workbook control upgrades
Add sheet:
ENFORCEMENT_SCALE
Values:
NOT_ENFORCED
PARTIAL
STRUCTURAL_ENFORCED
ENFORCED
Add README cockpit:
LAST_LEDGER_REFRESH: 2026-04-27
SYSTEM_STATE: EXECUTION_STABLE / TRUTH_ENFORCEMENT_IN_PROGRESS
PRIMARY_BLOCKER: U2_PROPAGATION_ENFORCEMENT
SECONDARY_BLOCKER: PASS_1_OUTPUT_FEASIBILITY
Add to ROADMAP_LANES:
BLOCKED_BY
Rule:
If BLOCKED_BY is not ENFORCED, item cannot move to ACTIVE.
Correct next execution order
1. Apply RCA/workbook hardening:
- LLR ambiguity fields
- ENFORCEMENT_SCALE
- README cockpit header
- BLOCKED_BY
- U2 RCA Batch 2
2. Apply minimal PASS1 feasibility patch:
- reduce output surface only enough to improve Pass 4 reachability
3. Execute U2 propagation enforcement:
- confidence derivation
- propagation profile
- score-confidence alignment
- anti-washing rule
- UI authority fusion
- persistence trace
- PV115 golden fixture
4. Re-run real production evaluation proof.
5. Only after U2:
- prompt depth upgrades
- meta-fiction / cultural texture / structural nuance improvements
- U3 contradiction detection
Final cockpit lines
BLOCK_B_ATOMICITY: ENFORCED.
RELIABILITY_GATE: ENFORCED.
DIALOGUE_ATTRIBUTION_GATE_V2: ENFORCED.
PHASE_1_OBSERVABILITY: STRUCTURAL_ENFORCED / EMPIRICAL_PARTIAL.
PASS_1_OUTPUT_FEASIBILITY: OPEN.
LLR_POST_STRUCTURAL_BLOCK / LLR-004: OPEN CLASSIFICATION TRACK.
U2_PROPAGATION_ENFORCEMENT: PRIMARY NEXT BLOCK.
EVALUATION_TRUTH_ENFORCEMENT: NOT COMPLETE.

## Complete-Partially-Pending
Complete / Partially Complete / Pending — Session Ledger
Status | Lane | Item | Enforcement_Level | Completed_Scope | Proof_Evidence | Remaining_Gap | Next_Action | Date | Notes | RCA_ID | CAUSE_TYPE | BLOCKED_BY
Completed | Persistence Boundary | Step 1.5 V2 boundary hardening / U1 Audit scope | ENFORCED — boundary scope | persistEvaluationResultV2 is the sole V2 persistence boundary; validation/gate/confidence happen before persistence; U1 Audit is honestly scoped to persistence boundary. | PR #240; merge ab611810; 4/4 boundary suite; production smokes 5cca06a2 and 01cbbf9e; QG fail 3ef78daf excluded as phase_1 | Full system audit trace beyond boundary remains separate. | Keep U1 Audit row as ENFORCED — persistence boundary scope only. | 2026-04-26 | Cockpit moved to 10/23 at this closeout point. | RCA-ATOMIC-PERSISTENCE-001 | DB_RPC | None
Completed | Atomicity | Block B atomic persistence delivered and proven | ENFORCED | Success path moved from artifact upsert + completion update to atomic RPC; ambiguity hotfix applied live and committed to source. | PR #241 RPC; PR #242 boundary switch; PR #243 ambiguity hotfix; DB function verified SECURITY DEFINER + service_role EXECUTE | None for Block B; monitor regression only. | Keep status ENFORCED; source/DB/runtime aligned. | 2026-04-26 | Production success proof closed the empirical gap. | RCA-ATOMIC-PERSISTENCE-001 | DB_RPC | None
Completed | Atomicity | Production success-path proof captured | ENFORCED | Controlled service-role smoke on manuscript 5800 completed phase_2 with gate_enforcement PASS and matching artifact row. | Job 29089ed6-0fc7-485b-a699-56498b950295; artifact af699bd8-1618-4971-a097-b4345f3e7733 | None for atomicity. | Use as canonical proof row. | 2026-04-26 | completed_at 2026-04-26T22:23:39.34Z; artifact source_hash recorded. | RCA-ATOMIC-PERSISTENCE-001 | DB_RPC | None
Completed | Reliability | 100k soak gate passed | ENFORCED | Stress soak processed 100,000 events with zero unclassified failures, zero wrong-location edits, zero lost writes, no non-canonical status, no silent fallback. | Evidence dir docs/operations/evidence/runs/2026-04-26T21-32-48-713Z; 9040 retries all handled | None for harness proof; keep it required for reliability lane. | Preserve gate:reliability / soak proof as release guard. | 2026-04-26 | Throughput 7058.657 events/sec, concurrency 10.
Completed | Dialogue Gate V2 | Diagnostic-grounded dialogue attribution gate implemented and locally proven | ENFORCED — gate-level deterministic | Lexical-only QG_DIALOGUE_ATTRIBUTION_UNDERAUDITED path replaced by marker OR diagnostic-grounded analysis; local tests green; post-fix reachable runs did not re-trigger QG_DIALOGUE_ATTRIBUTION_UNDERAUDITED. | PR #245; qualityGate.ts; analyzeDialogueAttribution; runPass3Synthesis; runPipeline; fixture PV115 | System-level reachability still blocked by upstream Pass 1/LLR on some manuscripts. | Keep DIALOGUE_ATTRIBUTION_GATE_V2 as gate-level ENFORCED, with reachability caveat. | 2026-04-27 | Do not confuse upstream non-determinism with dialogue gate failure. | RCA-DIALOGUE-GATE-001 | GATE_LOGIC | Upstream reachability only
Completed | Failure Envelopes | Canonical pipeline_failure_envelope now observable on current failure path | ENFORCED | Recent QG failure job 40b377de has envelope with failed_at=pass4 and pipeline_stage=pass4; older jobs lacked envelope as expected pre-fix baseline. | Job 40b377de-30af-4b86-9594-aceda2a5b4ba; older 5a413a7f and 3ef78daf are pre-fix/no-envelope baseline | Diagnostics propagation is separate and still needs fresh runtime lock. | Keep envelope row ENFORCED; do not overclaim diagnostics. | 2026-04-27 | This is the diagnostic surface for next investigations. | RCA-FAILURE-ENVELOPE-001 | OBSERVABILITY | Fresh diagnostics sample
Completed | Calibration | Corrected 5-run manuscript 5907 calibration executed | OBSERVED | 5-run calibration produced non-deterministic upstream outcomes: 2 complete, 2 PASS1_FAILED, 1 LLR_POST_STRUCTURAL_BLOCK. | Runs: failed 36s, complete 181s, failed 57s, complete 139s, LLR fail 46s | It did not prove full-pipeline determinism; it proved upstream blockers. | Use results to open Pass 1 feasibility and LLR tracks. | 2026-04-27 | Discard invalid earlier error_message polling attempt. | RCA-PASS1-TOKEN-001 | PROMPT_SCHEMA_BUDGET | Output surface reduction proof
Completed | Empirical Baseline | 7-day failure baseline collected | OBSERVED | Recent PASS1 failures cluster around finish_reason=length at completion_tokens=3500 with empty response; LLR_POST_STRUCTURAL_BLOCK observed separately. | 7-day counts: PASS1_FAILED=6; LLR_POST_STRUCTURAL_BLOCK=2; manuscripts 5832 and 5907 affected | Needs mitigation design and proof. | Create PASS_1_OUTPUT_FEASIBILITY track. | 2026-04-27 | This is token-budget/output-exhaustion, not dialogue gate. | RCA-PASS1-TOKEN-001 | PROMPT_SCHEMA_BUDGET | Output surface reduction proof
Completed | Evaluation Quality | PV115 Evaluation No. 3 critique synthesized | OBSERVED | Four systems converged: evaluation directionally correct but shallow; confidence is advisory rather than authoritative; U2 is the blocker. | Evaluation No. 3 PV115 Final V3; external AI consensus; repo trace | Implementation still pending. | Use PV115 as golden fixture for U2 fidelity tests. | 2026-04-27 | Accuracy target reframed as 99% honesty, not impossible 99% literary truth.
Completed | Planning | U2 implementation plan locked | SPEC COMPLETE | Concrete file list, rule logic, thresholds, test cases, and acceptance criteria defined. | qualityGate.ts, runPipeline.ts, runPass3Synthesis.ts, persistEvaluationResultV2.ts, warningClassification.ts, evaluation-result-v2.ts, confidenceDerivation.ts | No code implemented yet in this workbook state. | Begin one implementation PR. | 2026-04-27 | No more specification needed before coding.
Partially Complete | Phase 1 Observability | PHASE_1_OBSERVABILITY split from U1 Audit | STRUCTURAL/EMPIRICAL MIXED | Structured failure envelope exists for current QG path; PASS1/LLR diagnostic surface is improving, but diagnostics are not uniformly proven on every phase_1 failure class. | QG job 40b377de envelope true; PASS1/LLR baseline queried; prior PASS1 jobs had null diagnostics/envelope before patch path | Need fresh post-fix PASS1_FAILED proof with pipeline_failure_envelope populated and diagnostics as applicable. | Patch exact PASS1_FAILED markFailed route and run proof. | 2026-04-27 | Do not count phase_1 failures against U1 boundary enforcement. | RCA-PASS1-TOKEN-001 | PROMPT_SCHEMA_BUDGET | Output surface reduction proof
Partially Complete | Dialogue Diagnostics | pipeline_failure_diagnostics propagation implemented but not empirically locked | STRUCTURAL ENFORCED / EMPIRICAL PENDING | qualityGate.ts attaches diagnostics; runPipeline carries failure_details; code structure exists. | Repo trace: QualityGateCheck.diagnostics; runPipeline.failure_details; types support diagnostics | Fresh post-deploy failure sample with non-null pipeline_failure_diagnostics still needed. | Force/reproduce post-fix diagnostic-bearing failure and query DB. | 2026-04-27 | Old 40b377de lacks diagnostics because it predates wiring. | RCA-DIALOGUE-GATE-001 | GATE_LOGIC | Upstream reachability only
Partially Complete | Production Alignment Guard | Guard intentionally parked during dev | PARKED | Production Alignment Guard secrets were not configured by decision; dev work should not churn prod alignment settings. | Decision: leave Vercel/Supabase/GitHub prod guard secrets alone during dev | Will remain blind until production cutover. | Record as PARKED, not failed. | 2026-04-26 | Revisit at launch/prod alignment phase.
Partially Complete | PASS1 Output Feasibility | Pass 1 token budget failure isolated | FAILED / OPEN | PASS1_FAILED dominated by empty OpenAI response due finish_reason=length at max_output_tokens=3500; prompt_tokens around 4902/4791. | 7-day query; failures on manuscripts 5832/5907 | Root fix not implemented. | Measure prompt/output footprint, reduce Pass 1 output surface, then verify. | 2026-04-27 | Do not solve with generic retries or token cap only. | RCA-PASS1-TOKEN-001 | PROMPT_SCHEMA_BUDGET | Output surface reduction proof
Partially Complete | LLR | LLR_POST_STRUCTURAL_BLOCK observed as upstream blocker | OPEN | LLR_POST_STRUCTURAL_BLOCK appears in calibration as a pre-gate blocker separate from dialogue attribution gate. | 5-run calibration; 7-day counts show 2 LLR_POST_STRUCTURAL_BLOCK | Requires separate RCA/calibration. | Triage LLR-004/LLR post-structural criteria and registry behavior. | 2026-04-27 | Keep separate from dialogue gate. | RCA-LLR-004-001 | AMBIGUOUS | Classify subtype before fix
Pending | U2 | U2 Fidelity / Propagation Enforcement | PENDING | Confidence/weakness signals are still not hard control-flow authority; summary/UI can overstate certainty. | PV115 critique; repo trace confirms static-ish confidence and warning-only low-confidence behavior | Primary next block. | Implement U2 single PR in commit order: schema/types → qualityGate → runPipeline → Pass3 anti-washing → persistence trace → UI → tests. | 2026-04-27 | This is the Monday first task. | RCA-ATOMIC-PERSISTENCE-001 | DB_RPC | None
Pending | Pass 3 | Anti-washing synthesis constraint | PENDING | Pass 3 can sound cleaner/more confident than the score and evidence profile supports. | PV115: positive summary while pacing/theme/closure are weak | Needs deterministic gate/signal. | Require summary to reference at least one bottom-scoring weakness. | 2026-04-27 | Part of U2 PR.
Pending | UI Authority | Warning/high-confidence banner fusion | PENDING | UI authority is not yet fully bound to confidence topology and propagation severity. | warningClassification.ts trace | Needs update/test. | Block high-confidence banner when artifact PASS conflicts with low/mixed/weak confidence. | 2026-04-27 | Part of U2 PR.
Pending | Golden Fixture | PV115 golden fidelity fixture | PENDING | PV115 should prove that meta-fiction, Mexico parallel, dogs/environmental signaling, river force imagery, and deliberate withholding cannot be missed while confidence stays high. | Evaluation No. 3 critique | Fixture not yet implemented. | Add fixture-driven test; if those signals are missed, confidence cannot remain high. | 2026-04-27 | Golden fixture supports fidelity, not just schema.
Pending | Pass 1 | Output-surface reduction | PENDING | Pass 1 asks for too much output: likely too many anchors/rationales/recommendations/schema fields for long manuscripts. | PASS1_FAILED finish_reason=length at 3500 completion tokens | Needs design + test. | Measure prompt; remove recommendations/deep rationale from Pass 1; cap evidence to 0–1; shift depth to Pass 2/3. | 2026-04-27 | Quality-first fix is output reduction, not optimism. | RCA-PASS1-TOKEN-001 | PROMPT_SCHEMA_BUDGET | Output surface reduction proof
Pending | Prompt Depth | Reasoning depth improvements after U2 | PENDING | Prompts need explicit craft dimensions: meta-fiction, parallel structures, animal/environmental signaling, withholding, cultural texture. | PV115 critique | Should follow U2 truth-control layer. | Update pass1-craft.ts and pass2-editorial.ts after U2 enforcement. | 2026-04-27 | Prompt depth without U2 can create polished overclaiming.
Pending | U3 | Contradiction detection / Gate 15.2 | PENDING | Contradictions can still remain unresolved and clean/high-confidence. | Existing U3 roadmap | Not implemented. | Build detector/taxonomy/artifact fields/gate/UI after U2. | 2026-04-27 | Still part of remaining 7 open rows.
Partially Complete | U2 Fidelity | RCA-U2-003 derived confidence | PARTIAL | Deterministic confidence derivation implemented/tested in local/branch context; not yet final under doctrine. | Focused/broad local tests reportedly green; remote branch has U2 propagation package; no live server/API artifact proof yet. | Final local changes must be committed/pushed; live proof must show governance.confidence_label + confidence_reasons from evidence profile. | Commit/push, verify PR diff, run live proof; only then mark RESOLVED. | 2026-04-28 | Phase 2E/RLS evidence must not be used as U2 closure proof. | RCA-U2-003
Partially Complete | U2 Fidelity | RCA-U2-006 evidence anchor enforcement | PARTIAL | Anchor enforcement exists locally and local tests reportedly pass; not yet remote/live-proven. | Local NO_TEXTUAL_ANCHOR/runPass2 anchor enforcement proof; remote branch did not show those files at last check. | Commit/push anchor enforcement files and capture live proof that missing anchors downgrade/hold. | Commit/push, verify remote contains NO_TEXTUAL_ANCHOR + test, run live server/API proof. | 2026-04-28 | Keep scope narrow: anchor/citation enforcement only, not score-confidence or full confidence derivation. | RCA-U2-006

## CURRENT_STATE
CURRENT_STATE — 17 / 23 ENFORCED
# | System Row | Level | Proof / Evidence | Current Meaning | Remaining Gap | Next Action | Date | RCA_ID | CAUSE_TYPE | BLOCKED_BY
1 | Single V2 persistence boundary | ENFORCED | PR #238 + #240; guard and boundary tests | Only boundary may persist V2 artifacts. | None for boundary scope. | Preserve guard. | 2026-04-26 | RCA-ATOMIC-PERSISTENCE-001 | DB_RPC | None
2 | Step 1.5 structural validation | ENFORCED | Live production SQL + code proof: job 533a77a5-11cd-4b06-9167-41332cd12390 returned progress.gate_enforcement populated (PASS, confidence high, reason_codes=[]); artifact_schema=evaluation_result_v2; structural validator runs on raw EvaluationResultV2; PASS regression 6/6. | Validation precedes persistence in covered path; raw PASS shape proof is resolved with production-data evidence. | None for covered PASS path. | Proceed to U2 execution: close RCA-U2-003 and RCA-U2-006. | 2026-04-27 | RCA-BOUNDARY-SHAPE-001 | PROOF_GAP_CLOSED | NONE
3 | Fail-closed V2 behavior | ENFORCED | No output/persistence/render unless gates pass | Invalid state blocked at boundary. | None for covered path. | Keep tests required. | 2026-04-26
4 | U1 Formula: canonical inputs only | ENFORCED | Boundary inputs and validator/gate contracts | Confidence inputs are constrained in boundary path. | Broader release semantics still tracked separately. | Keep U1 row scoped. | 2026-04-26
5 | U1 Authority: single confidence path | ENFORCED | deriveConfidence used in boundary flow | No shadow confidence on V2 persistence path. | Full UI confidence authority handled by U2. | Do not duplicate confidence writes. | 2026-04-26
6 | U1 Audit: penalty trace emitted | ENFORCED — boundary scope | U1 Audit closure; job 3ef78daf excluded as phase_1 not boundary | Audit applies to persistence boundary, not all pipeline failures. | Separate phase1 observability remains. | Keep wording exact. | 2026-04-26
7 | Atomic persistence RPC | ENFORCED | PR #241; DB function persist_evaluation_v2_atomic | Artifact + completion are atomic in success path. | None after hotfix. | Keep migration in source. | 2026-04-26 | RCA-ATOMIC-PERSISTENCE-001 | DB_RPC | None
8 | Atomic boundary switch | ENFORCED | PR #242; success path uses RPC | Sequential write split removed. | None after live proof. | Monitor CI. | 2026-04-26 | RCA-ATOMIC-PERSISTENCE-001 | DB_RPC | None
9 | Atomic ambiguity hotfix | ENFORCED | PR #243; live DB hotfix; #variable_conflict use_column | Column ambiguity fixed and source/DB aligned. | None. | Merge/source state closed. | 2026-04-26 | RCA-ATOMIC-PERSISTENCE-001 | DB_RPC | None
10 | Production atomic proof | ENFORCED | Job 29089ed6 complete; artifact af699bd8 exists | Success path works end-to-end. | None. | Use as proof row. | 2026-04-26 | RCA-ATOMIC-PERSISTENCE-001 | DB_RPC | None
11 | Reliability soak | ENFORCED | 100k soak pass, 0 lost/wrong/unclassified writes | Reliability gate is proven. | None. | Keep as release guard. | 2026-04-26
12 | Public job auth gate | ENFORCED | jobs:smoke:real 401 without auth | Public unauthenticated job creation blocked. | None. | Preserve. | 2026-04-26
13 | Dev→prod safety guard | ENFORCED | dev refused against prod Supabase without bypass | Unsafe dev-prod mutation blocked. | None. | Preserve. | 2026-04-26
14 | Canonical runtime authority guard | ENFORCED | spine/docs runtime guards green | Docs/runtime authority remains aligned. | None. | Preserve. | 2026-04-26
15 | Dialogue Attribution Gate V2 | ENFORCED — gate-level | Post-fix reachable runs show no QG_DIALOGUE_ATTRIBUTION_UNDERAUDITED recurrence | Gate logic no longer lexical-only. | Upstream reachability still constrained. | Do not conflate Pass1/LLR with dialogue gate. | 2026-04-27 | RCA-DIALOGUE-GATE-001 | GATE_LOGIC | Upstream reachability only
16 | Pipeline failure envelope surface | ENFORCED | Current QG job has failed_at/pass4 and pipeline_stage/pass4 envelope | Failure modes are queryable by job ID. | Diagnostics proof separate. | Use for triage queries. | 2026-04-27
17 | Quality gate diagnostics propagation | STRUCTURAL ENFORCED / EMPIRICAL PENDING | Code supports diagnostics, but fresh runtime non-null diagnostics still pending | Diagnostics are wired but not fully runtime-locked. | Need post-fix diagnostic-bearing failure. | Run targeted failure proof. | 2026-04-27 | RCA-FAILURE-ENVELOPE-001 | OBSERVABILITY | Fresh non-null diagnostics sample
18 | PHASE_1_OBSERVABILITY | PARTIAL | Phase1 failures separated from U1; PASS1/LLR baseline available | Phase1 trace is a distinct row, not a boundary defect. | Need fresh PASS1 envelope/diagnostics proof after exact catch-site patch. | Patch markFailed route and smoke. | 2026-04-27
19 | PASS_1_OUTPUT_FEASIBILITY | FAILED / OPEN | PASS1_FAILED finish_reason=length at 3500 completion tokens | System can be correct but unreachable on long inputs. | Root fix not implemented. | Measure footprint and reduce output surface. | 2026-04-27
20 | LLR_POST_STRUCTURAL_BLOCK | AMBIGUOUS | Observed in calibration and 7-day baseline | Separate pre-gate blocker exists. | Subtype not classified yet; must not be treated as model-only failure. | Capture failing Pass2 payload; classify subtype; move AMBIGUOUS → RESOLVED only after subtype is proven. | 2026-04-27 | RCA-LLR-004-001 | AMBIGUOUS | Failing Pass2 payload classification
21 | U2 Fidelity / Propagation | NOT_READY | PV115 moved to VERIFICATION_ARTIFACTS as proof fixture, not RCA. | Fixture validates U2 closures on real signals. | Not executable as RCA; depends on U2 RCA closures. | Track in VERIFICATION_ARTIFACTS; run after U2 gate surfaces exist. | 2026-04-27 | PV115-GOLDEN-FIXTURE | VERIFICATION_ARTIFACT | RCA-U2-001; RCA-U2-002; RCA-U2-004; RCA-U2-005; RCA-U2-006
22 | U3 contradiction detection | PENDING | Existing roadmap lane | Contradiction logic not implemented. | Pending after U2. | Schedule after U2. | 2026-04-27
23 | PV115 golden fidelity fixture | PENDING | Evaluation No. 3 critique | No golden fixture yet locks missed craft signals. | Fixture not implemented. | Add to U2 test suite. | 2026-04-27
31 | U2 Confidence derivation | PARTIAL — REMOTE IMPLEMENTATION / LIVE_PROOF_PENDING | Remote branch includes commit 8ecdde70 with deterministic confidence implementation; focused local tests green. Live server/API artifact proof is still pending. | Confidence derivation is implemented and pushed, but not RESOLVED under doctrine until live proof shows governance.confidence_label + confidence_reasons in persisted/API artifact. | Live proof missing. | Run U2 closure proof; capture governance.confidence_label, confidence_reasons, propagation_summary, and progress.gate_enforcement. | 2026-04-28 | RCA-U2-003 | SYSTEM | LIVE_PROOF_PENDING
32 | U2 Propagation layer | NOT_STARTED | RCA-U2-004 inserted | Per-criterion weakness must propagate to artifact authority. | Depends on derived confidence. | Close RCA-U2-004 after U2-003. | 2026-04-27 | RCA-U2-004 | SYSTEM | RCA-U2-003
33 | U2 Score-confidence enforcement | NOT_STARTED | RCA-U2-001 inserted | Low confidence must constrain score authority. | Depends on derived confidence. | Close RCA-U2-001 after U2-003. | 2026-04-27 | RCA-U2-001 | SYSTEM | RCA-U2-003
34 | U2 Evidence anchor enforcement | PARTIAL — REMOTE IMPLEMENTATION / LIVE_PROOF_PENDING | Remote branch includes commit 8ecdde70 with runPass2 NO_TEXTUAL_ANCHOR/anchor enforcement and runPass2.anchor-enforcement.test.ts; focused local tests green. | Anchor enforcement is implemented and pushed, but not RESOLVED until live/real-path proof shows reason_codes / NO_TEXTUAL_ANCHOR behavior when applicable. | Live proof missing. | Run U2 closure proof; capture anchor-enforcement reason codes and persisted/API artifact evidence. | 2026-04-28 | RCA-U2-006 | MODEL + SYSTEM | LIVE_PROOF_PENDING
35 | U2 Summary anti-washing | NOT_STARTED | RCA-U2-002 inserted | Pass3 summary must not smooth lowest-scoring weakness away. | Depends on evidence anchor enforcement. | Close RCA-U2-002 after U2-006. | 2026-04-27 | RCA-U2-002 | SYSTEM | RCA-U2-006
36 | U2 UI authority lock | NOT_STARTED | RCA-U2-005 inserted | Report UI must not show high-confidence authority on weak/mixed artifact. | Depends on propagation layer. | Close RCA-U2-005 after U2-004. | 2026-04-27 | RCA-U2-005 | SYSTEM | RCA-U2-004
37 | BOUNDARY_VALIDATION_SHAPE_GAP | RESOLVED | Live SQL evidence: complete job 533a77a5-11cd-4b06-9167-41332cd12390 has progress.gate_enforcement populated; artifact_schema=evaluation_result_v2; completed_at=2026-04-27T04:26:09.436+00:00. | Boundary raw-shape concern resolved; prior gate_enforcement:null confusion was a query-shape issue (top-level column vs progress JSONB), not a code defect. | None. | Keep regression and query progress->'gate_enforcement' for future live checks. | 2026-04-27 | RCA-BOUNDARY-SHAPE-001 | PROOF_GAP_CLOSED | NONE

## U_GATES_ENFORCEMENT
U_GATES_ENFORCEMENT — U1 advanced, U2 now primary blocker
Gate | Area | Check | Must | Level | Owner | Target PR / Branch | Target Date | Can Fail Silently? | Gap | Proof
U1 | Formula | Canonical inputs only | Y | ENFORCED | Mike | Merged (#240) | Done | NO | Scoped to persistence boundary; broader UI authority handled by U2 | Boundary guard + tests
U1 | Formula | C1–C5 penalties implemented | Y | ENFORCED | Mike | Merged (#240) | Done | NO | Boundary-scope confidence penalties enforced | Boundary tests
U1 | Authority | Single deriveConfidence path | Y | ENFORCED | Mike | Merged (#240) | Done | NO | No shadow confidence in V2 persistence path | Code search + guard
U1 | Release | Confidence controls boundary release | Y | ENFORCED — boundary scope | Mike | Merged (#240) | Done | NO | UI/product authority still U2 | Boundary fail-closed tests
U1 | Audit | Penalty trace emitted | Y | ENFORCED — boundary scope | Mike | U1 Audit closure | Done | NO | Phase1 failures are separate PHASE_1_OBSERVABILITY row | U1 closure + production IDs
U1 | Proof | Bad cases lower/block confidence | Y | ENFORCED — boundary scope | Mike | Merged (#240) | Done | NO | Golden breadth can expand later | Boundary fixtures
U2 | Signals | Pass 1/2 weakness flags | Y | OBSERVED | Mike | Next: U2 fidelity PR | 2026-04-27 | YES | Signals exist but do not fully control artifact authority | PV115 critique + repo trace
U2 | Handoff | Weakness reaches governance | Y | PENDING | Mike | Next: U2 fidelity PR | 2026-04-27 | YES | Propagation summary not enforced | Add propagation_summary
U2 | Penalty | Weakness reduces confidence/validity | Y | PENDING | Mike | Next: U2 fidelity PR | 2026-04-27 | YES | Confidence can be decorative | Derived confidence rules
U2 | Non-bypass | Pass 3 cannot discard weakness | Y | PENDING | Mike | Next: U2 fidelity PR | 2026-04-27 | YES | Summary can wash over low scores | QG_SUMMARY_OMITS_WEAKNESS
U2 | Artifact | Propagation summary emitted | Y | PENDING | Mike | Next: U2 fidelity PR | 2026-04-27 | YES | No persisted propagation trace yet | persistEvaluationResultV2 gate_enforcement
U2 | Proof | Weak case cannot stay clean/high | Y | PENDING | Mike | Next: U2 fidelity PR | 2026-04-27 | YES | Need contradiction/golden fixtures | PV115 fixture
U3 | Detector | Contradiction module exists | Y | PENDING | Mike | Post-U2 | TBD | YES | No detector | Unit tests
U3 | Taxonomy | Rules live in code | Y | PENDING | Mike | Post-U2 | TBD | YES | No taxonomy | Canon/code map
U3 | Artifact | contradictionCount/details emitted | Y | PENDING | Mike | Post-U2 | TBD | YES | No fields | Schema test
U3 | Governance | QualityGate reads contradictions | Y | PENDING | Mike | Post-U2 | TBD | YES | Not wired | Integration
U3 | Confidence | Contradictions reduce confidence | Y | PENDING | Mike | Post-U2 | TBD | YES | No penalty | Regression
U3 | UI | Contradictions surface as DISPUTED | Y | PENDING | Mike | Post-U2 | TBD | YES | No UI mapping | UI test
U3 | Proof | Contradiction cannot pass clean/high | Y | PENDING | Mike | Post-U2 | TBD | YES | Need golden case | Golden harness
QG | Dialogue Attribution | Gate uses diagnostic truth, not lexical-only keywords | Y | ENFORCED — gate-level | Mike | PR #245 | Done | NO | Reachability constrained by upstream Pass1/LLR, not gate | Post-fix reached-gate runs
QG | Diagnostics | Quality gate diagnostics persist on failure path | Y | STRUCTURAL ENFORCED / EMPIRICAL PENDING | Mike | PR #245 + proof | TBD | YES | Need fresh non-null diagnostics sample | DB query for pipeline_failure_diagnostics
CERT | System | Invalid escape rate = 0 | Y | PENDING | Mike | Certification proof run | TBD | YES | U2/U3/golden proof not complete | Fixed scenarios
CERT | System | U1/U2/U3 fully enforced | Y | PENDING | Mike | Certification proof run | TBD | YES | U2/U3 pending | All gate proofs

## EXECUTION_BLOCK
Current Execution Block: U2 Fidelity Enforcement = Close Six RCAs
Seq | Active Now? | RCA_ID | Work Item | Layer | Current Level | Target Level | Blocking Gap | Done Criteria | Status | DEPENDS_ON_RCA
1 | YES | RCA-U2-003 | Confidence derivation | Pipeline / Confidence | PARTIAL — REMOTE/TEST PROOF | ENFORCED | Implementation is pushed in commit 8ecdde70, but live server/API artifact proof is missing. | governance.confidence_label and reasons derived from evidence profile in committed branch plus live server/API artifact proof. | PARTIAL — LIVE_PROOF_PENDING | NONE
2 | YES | RCA-U2-004 | Propagation layer | Pipeline / Gate | NOT_STARTED | ENFORCED | Weak criteria do not affect overall artifact authority | Propagation profile + upstreamIntegrity strong¦mixed¦weak computed and gate-consumable | NEXT | RCA-U2-003
3 | YES | RCA-U2-001 | Score-confidence enforcement | Quality Gate | NOT_STARTED | ENFORCED | Score can overclaim when confidence is low | QG_FIDELITY_SCORE_CONFIDENCE_MISMATCH tested and enforced | NEXT | RCA-U2-003
4 | YES | RCA-U2-006 | Evidence anchor enforcement | Pass2 / Quality Gate | PARTIAL — REMOTE/TEST PROOF | ENFORCED | Anchor enforcement is pushed in commit 8ecdde70, but live proof is not yet complete. | NO_TEXTUAL_ANCHOR/anchor enforcement committed, tested, and proven on real server/API path. | PARTIAL — LIVE_PROOF_PENDING | NONE
5 | YES | RCA-U2-002 | Pass3 anti-washing | Synthesis | NOT_STARTED | ENFORCED | Summary can omit bottom-scoring weakness | Summary references weakest cluster or QG_SUMMARY_OMITS_WEAKNESS fires | NEXT | RCA-U2-006
6 | YES | RCA-U2-005 | UI authority lock | UI Truth | NOT_STARTED | ENFORCED | High-confidence UI can overstate weak artifact | PASS + low/weak/mixed confidence cannot render high-confidence banner | NEXT | RCA-U2-004
7 | YES | PV115-GOLDEN-FIXTURE | Golden fixture validation (verification artifact, not RCA) | Proof / Verification Artifact | NOT_READY | ENFORCED | PV115 can still miss real signals until U2 RCAs close | Fixture passes only after required U2 RCAs close; PROMOTION_RULE must pass before U2 is ENFORCED. | NEXT | RCA-U2-001; RCA-U2-002; RCA-U2-004; RCA-U2-005; RCA-U2-006
8 | PARALLEL | RCA-PASS1-TOKEN-001 | PASS1_OUTPUT_FEASIBILITY minimal patch | Pipeline Feasibility | OPEN | OBSERVED | PASS1 finish_reason=length can block proof reachability | Only minimal output-surface reduction; no latency side quest | OPEN | NONE
9 | PARALLEL | RCA-LLR-004-001 | LLR_POST_STRUCTURAL_BLOCK triage | Governance / LLR | AMBIGUOUS | RESOLVED | LLR-004 can block before U2 evidence is observable | Classify MODEL_OUTPUT_INVALID vs RULE_TOO_STRICT vs REGISTRY_DRIFT; AMBIGUOUS → RESOLVED. | AMBIGUOUS | NONE
10 | NO | POST-U2-PROMPT-DEPTH | Prompt reasoning depth upgrades | Prompt Quality | SPECIFIED | OBSERVED | Prompts miss meta-fiction/parallel/animal/env/withholding/cultural texture | Update prompts only after U2 truth-control closes | WAIT | U2 RCAs
13 | REFERENCE | PV115-GOLDEN-FIXTURE | Verification artifact tracking | Proof | NOT_READY | READY | PV115 was previously pseudo-RCA | Tracked in VERIFICATION_ARTIFACTS; remains non-RCA proof item | NOT_READY | U2 RCAs

## ROADMAP_LANES
Lane | Purpose | Current Truth | Primary Gap | Next Move | Do Not Do Yet | BLOCKED_BY | DEPENDS_ON_RCA
System Liveness | Keep jobs moving reliably and under latency target | Stable baseline; auth and dev/prod guards verified | Monitor only | Protect with smoke/reliability gates | Further latency tuning before truth enforcement
Persistence / Boundary | Make invalid artifact persistence impossible | ENFORCED; atomic success path proven; boundary raw-shape gap RESOLVED with live DB evidence | None for covered PASS persistence path | Preserve PR #240–#243 guard/tests; keep PASS-path gate_enforcement regression; future live checks must query progress->'gate_enforcement'. | Assume future schema changes are covered without rerunning raw PASS shape proof | RCA-BOUNDARY-SHAPE-001 | RCA-ATOMIC-PERSISTENCE-001; RCA-BOUNDARY-SHAPE-001
Governance | Make invalid or overconfident output impossible to present | Execution gates strong; U2-003/U2-006 are implemented and pushed, but live proof pending. | U2-003/U2-006 need live server/API proof before closure. | Run U2 live proof and capture persisted/API artifact fields before RESOLVED. | More prompt work before U2 | U2 RCA closure order | RCA-U2-003; RCA-U2-004; RCA-U2-001; RCA-U2-006; RCA-U2-002; RCA-U2-005
Artifact Quality | Make output evidence-bound and not shallow | Structurally complete; U2 anchor/confidence enforcement is implemented+pushed but not live-proven. | Evidence→confidence→score→summary still pending live closure proof. | Treat U2-003/U2-006 as PARTIAL REMOTE; do not promote PV115 until live proof and downstream RCAs close. | Treat polished summary as proof of accuracy | U2 RCA closure order | RCA-U2-006; RCA-U2-002; RCA-U2-001; RCA-U2-004
Confidence / CEL | Turn confidence into deterministic control-flow authority | U1 boundary enforced; U2 confidence derivation is implemented+pushed but live-proof pending. | Need live artifact proof for deterministic confidence authority. | Close RCA-U2-003 only after live proof, then proceed to U2-004. | Let model confidence drive release authority | U2 RCA closure order; PV115 waits on U2 RCAs | RCA-U2-003; RCA-U2-004; RCA-U2-005; PV115-GOLDEN-FIXTURE
Pipeline Feasibility | Ensure the system reaches gates reliably | Pass1 output budget fails on longer manuscripts | finish_reason=length at 3500 tokens | Measure/reduce Pass1 output surface | Generic retries or token bump as sole fix | PASS1_OUTPUT_FEASIBILITY | RCA-PASS1-TOKEN-001
Dialogue Attribution Gate V2 | Prevent false QG_DIALOGUE_ATTRIBUTION_UNDERAUDITED while preserving fail-closed behavior | Gate-level ENFORCED on reachable post-fix runs | Upstream reachability can mask proof | Keep gate; use diagnostics if future failures recur | Rework gate based on pre-fix jobs | Upstream reachability only | RCA-DIALOGUE-GATE-001
Failure Diagnostics | Make failures queryable and causal | pipeline_failure_envelope works; diagnostics structural only | Need fresh non-null pipeline_failure_diagnostics sample | Run targeted post-fix diagnostic failure proof | Call diagnostics enforced from old jobs | Fresh non-null diagnostics sample | RCA-FAILURE-ENVELOPE-001
User UI | Show users system truth clearly | Lifecycle visible; truth authority not fully fused | warningClassification must obey confidence topology | Block high-confidence UI when upstream is weak/mixed | Decorative confidence banners | U2 propagation topology | RCA-U2-005 depends on RCA-U2-004
Admin Ops | Expose process/subprocess failures | Ops useful but secondary | Not primary blocker | Build after U2/Pass1 tracks stabilize | Admin UX before truth state is locked | PASS1_OUTPUT_FEASIBILITY | RCA-PASS1-TOKEN-001
Canon / Docs | Keep doctrine aligned to code | Canon strong; system state must stay committed | Need persistent current ledger | Commit/update SYSTEM_STATE or workbook each block | Rely on chat memory
U3 Contradiction Detection | Detect and surface contradictions | Pending | No detector/taxonomy/runtime gate | Schedule after U2 | Mix with U2 initial PR

## CANON_CODE_MAP
Canon Rule / Invariant | Current Enforcement | Can Fail Silently? | Primary Code Boundary | Proof Required | Notes
Only V2 boundary may persist evaluation artifacts | ENFORCED | NO | persistEvaluationResultV2.ts; guard script | Boundary guard + mutation tests | PR #240 / Step 1.5.
Artifact + completion success path is atomic | ENFORCED | NO | persist_evaluation_v2_atomic RPC | Production job + artifact proof | PR #241–#243; job 29089ed6; artifact af699bd8.
QualityGate must run before persistence | ENFORCED | NO | persistEvaluationResultV2.ts | Fail-closed tests | Invalid artifact cannot persist as complete.
All 13 canonical criteria must exist exactly once | OBSERVED | YES | evaluation-result-v2 schema / validators | Schema + mutation tests | Canon remains 13 criteria; no 14th criterion without formal canon change.
Scores are integer 0–10 only | OBSERVED | YES | validator / qualityGate | Unit + artifact snapshot | U2 will add score-confidence constraints.
Evidence must control confidence | PENDING | YES | qualityGate.ts / confidenceDerivation.ts | U2 propagation tests | Core fidelity gap.
Low confidence cannot support high score/authority | PENDING | YES | qualityGate.ts / warningClassification.ts | QG_FIDELITY_SCORE_CONFIDENCE_MISMATCH | Proposed U2 rule.
Pass 3 cannot wash over weaknesses | PENDING | YES | runPass3Synthesis.ts + qualityGate.ts | QG_SUMMARY_OMITS_WEAKNESS | Summary must cite bottom-scoring weakness cluster.
UI can only show what governance has proven | PENDING | YES | warningClassification.ts | PASS + low confidence contradiction test | High-confidence banner must obey confidence topology.
Dialogue rationale must prove attribution/rendering analysis | ENFORCED — gate-level | NO | qualityGate.ts / analyzeDialogueAttributionForGate | Post-fix reached-gate proof | PR #245; upstream reachability caveat.
Pipeline failure envelope must persist for terminal failures | ENFORCED | NO | processor markFailed / failure finalizer | DB query job 40b377de and fresh failures | Diagnostics trace is separate.
Quality-gate diagnostics must persist when available | STRUCTURAL ENFORCED / EMPIRICAL PENDING | YES | QualityGateCheck.diagnostics → runPipeline.failure_details | Fresh non-null diagnostics failure sample | Do not overclaim from pre-fix jobs.
Pass 1 output must fit bounded response budget | FAILED / OPEN | YES | Pass1 prompt/output contract | finish_reason length elimination proof | PASS1_OUTPUT_FEASIBILITY track.
Contradictions must be detected and surfaced | PENDING | YES | Gate 15.2 detector / QualityGate | Contradiction golden set | U3 after U2.

## SOURCE_INDEX
Source | Type | Use In This Workbook | Status | Notes
PR #240 | GitHub PR | Step 1.5 persistence boundary/U1 Audit boundary scope | Merged | Merge ab611810; boundary suite 4/4.
PR #241 | GitHub PR | Atomic RPC migration | Merged | persist_evaluation_v2_atomic created.
PR #242 | GitHub PR | Boundary success path switched to atomic RPC | Merged | Sequential write path removed.
PR #243 | GitHub PR | Atomic RPC ambiguity hotfix source alignment | Merged | Fix for column reference job_id ambiguity.
PR #245 | GitHub PR | Dialogue Attribution Gate V2 | Merged / gate-level enforced | Diagnostic-grounded gate; local + reachable runtime proof.
Job 29089ed6-0fc7-485b-a699-56498b950295 | Supabase evaluation_jobs | Atomic production success-path proof | Complete | status complete, phase_2, gate_enforcement PASS.
Artifact af699bd8-1618-4971-a097-b4345f3e7733 | Supabase evaluation_artifacts | Atomic artifact proof | Persisted | artifact_type/version evaluation_result_v2.
100k soak run 2026-04-26T21-32-48-713Z | Evidence artifact | Reliability gate proof | Pass | 100000 events, 0 lost/wrong/unclassified.
Job 40b377de-30af-4b86-9594-aceda2a5b4ba | Supabase evaluation_jobs | Post-fix QG envelope proof | Failure with envelope | failed_at/pass4 and pipeline_stage/pass4; diagnostics null.
Jobs 5a413a7f / 3ef78daf | Supabase evaluation_jobs | Pre-fix no-envelope baseline | Historical | Do not use against current envelope work.
Manuscript 5907 calibration | Production calibration | Dialogue gate reachability / upstream blocker proof | Executed / non-deterministic | 2 complete, 2 PASS1_FAILED, 1 LLR_POST_STRUCTURAL_BLOCK.
7-day failure query | DB empirical query | PASS1/LLR baseline | Current baseline | PASS1_FAILED=6, LLR_POST_STRUCTURAL_BLOCK=2.
Evaluation No. 3 PV115 Final V3 critique | Evaluation review | U2 fidelity/propagation diagnosis | Accepted as planning input | Used to define PV115 golden fixture and U2 scope.
RevisionGrade canon / NOMENCLATURE / job contract | Docs | Criteria count and lifecycle status contracts | Binding | 13 criteria; statuses queued/running/complete/failed.
This chat session | Conversation | Completed/partial/pending session truth | Current source | Use workbook as persistent state after export.
Local-vs-remote U2 verification | Repo/workspace assessment | U2-003/U2-006 closure status | Current | Local workspace edits/tests exist, but remote branch/proof path is not sufficient to mark RESOLVED; use PARTIAL until commit/push + live proof.
Branch feat/u2-propagation-enforcement @ 35f933a | GitHub branch check | Remote truth check | Current | Remote branch was 1 commit ahead of main; changed files did not include runPass2.anchor-enforcement.test.ts / NO_TEXTUAL_ANCHOR at last remote check.
ROADMAP.md | Repo markdown roadmap | Roadmap contract status | STALE / NEEDS UPDATE | Still describes older Step 0/1/1.5 contract and does not reflect RCA-led U2 Batch 2, boundary live proof closure, or U2-003/U2-006 partial status.
Commit 8ecdde70 | GitHub commit | U2-003/U2-006 remote implementation proof | Pushed | feat(u2): enforce deterministic confidence and anchor validation; adds runPipeline/runPass2/types/test surfaces.
Commit ca12ade4 | GitHub commit | ROADMAP.md status precision update | Pushed | docs(roadmap): update U2 status after remote implementation push; records PARTIAL REMOTE IMPLEMENTATION / LIVE_PROOF_PENDING.
Phase 2E evidence logs | Evidence logs | Not valid for U2 RCA closure | Do not use for U2 closure | Phase 2E/RLS evidence may remain a separate proof class; not closure evidence for U2-003/U2-006.

## ROADMAP_ARCHIVE_KEY
# | Action Item | Original Status | Current Session Reframe | Current Level | Where Now | Success Looks Like | Superseded By
1 | Step 0 / persistence boundary | COMPLETE | Now actually ENFORCED at boundary scope after PR #240 | ENFORCED | CURRENT_STATE rows 1–6 | Invalid artifacts cannot persist | PR #240
2 | Atomicity hardening | OPEN/PENDING | Completed and empirically proven after PR #241–#243 | ENFORCED | CURRENT_STATE rows 7–10 | Artifact and job completion are all-or-nothing | Block B Atomicity
3 | Dialogue Attribution Gate V2 | PR OPEN / TEST VERIFIED | Gate-level ENFORCED; upstream reachability caveat remains | ENFORCED — gate-level | CURRENT_STATE row 15 | No false QG_DIALOGUE_ATTRIBUTION_UNDERAUDITED on reachable runs | PR #245
4 | Quality-gate diagnostics | WIRED LOCALLY | Structural but fresh empirical diagnostics sample still pending | STRUCTURAL ENFORCED / EMPIRICAL PENDING | CURRENT_STATE row 17 | New failed gate row has non-null diagnostics | Diagnostics proof
5 | Phase 1 Observability | NONE | Separated from U1; mixed/partial until fresh PASS1 proof is locked | PARTIAL | CURRENT_STATE row 18 | PASS1/LLR failures emit canonical envelope and useful diagnostics | PASS1 catch-site work
6 | Pass 1 token budget | Not explicit | Now primary feasibility blocker | FAILED / OPEN | CURRENT_STATE row 19 | finish_reason=length eliminated for failing manuscript class | PASS_1_OUTPUT_FEASIBILITY
7 | U2 propagation | PENDING | Now the next mandatory block | PENDING | EXECUTION_BLOCK rows 1–7 | Evidence controls confidence/score/summary/UI | U2 PR
8 | Prompt reasoning depth | PENDING | Important but intentionally post-U2 | PENDING | ROADMAP_LANES | Prompts look for meta-fiction/parallel/dogs/withholding/cultural texture | Prompt depth PR after U2
9 | U3 contradiction detection | PENDING | Still pending after U2 | PENDING | U_GATES_ENFORCEMENT | Contradictions cannot pass clean/high | Gate 15.2

## ROOT_CAUSE_ANALYSIS
RCA_ID | ISSUE_KEY | SYSTEM_AREA | STAGE | SYMPTOM | ROOT_CAUSE | CAUSE_TYPE | RULE_STRICTNESS_FLAG | ENFORCEMENT_VS_CALIBRATION | IMPACT | FIX | FILES_CODE_SURFACE | E2E_STAGES | SCRIPTS_PROOF_SURFACE | STATUS | EVIDENCE | BLOCKED_BY | LAST_UPDATED | NEXT_ACTION | DEPENDS_ON_RCA
RCA-PASS1-TOKEN-001 | PASS1_OUTPUT_FEASIBILITY | Pass1 / OpenAI output budget | Pass1 | finish_reason=length / empty response / jobs fail before reliable downstream gates | Pass1 output surface exceeds practical token/output budget on longer manuscripts; evidence anchors + deep reasoning + recommendations inflate response. | PROMPT_SCHEMA_BUDGET | MEDIUM | ENFORCEMENT | Reduces Pass4 reachability and blocks empirical proof of U2/gate changes on longer manuscripts. | Reduce Pass1 output surface: one anchor where feasible, remove recommendations from Pass1, move deep reasoning downstream, classify truncation explicitly. | lib/evaluation/pipeline/runPass1.ts; lib/evaluation/pipeline/prompts/pass1-craft.ts; lib/evaluation/pipeline/runPipeline.ts; lib/llm/jsonParseBoundary.ts | E2E-04 pass1 + pass2; E2E-10 proof harness | scripts/e2e-golden-run.sh; scripts/check-e2e-summary.mjs; scripts/pipeline/run-phase2-7-real-run.ts; scripts/jobs-smoke-service-role.mjs | OPEN | Multiple observed PASS1 failures; finish_reason=length; completion token ceiling behavior discussed in session. | None; parallel minimal feasibility work while U2 RCA is defined. | 2026-04-27 | Implement minimal safe Pass1 output-surface reduction and add truncation classification proof.
RCA-LLR-004-001 | LLR-004 | Pass2 / Lessons Learned | Pass2 → post_diagnostic | LLR_POST_DIAGNOSTIC_BLOCK at Pass2; job fails before report and before U2 can be exercised. | UNKNOWN until inspected: could be invalid model diagnostics, rule strictness/calibration issue, or canon/registry mapping drift. | AMBIGUOUS | HIGH | AMBIGUOUS | Blocks pipeline before quality gate; can hide whether later governance/UI fixes work; must not be misclassified as only model failure. | Pull failing Pass2 output; compare line-by-line against ACTIVE_RULES.ts and canon registry; classify subtype before tuning prompt/rule/registry. | lib/evaluation/pipeline/runPass2.ts; lib/evaluation/pipeline/prompts/pass2-editorial.ts; lib/governance/lessonsLearned/ACTIVE_RULES.ts; lib/governance/canonRegistry.ts | E2E-04 pass1 + pass2; E2E-06 quality_gate | scripts/e2e-golden-run.sh; scripts/pipeline/run-phase2-7-real-run.ts; __tests__/lib/evaluation/processor.canonical-pipeline.test.ts | AMBIGUOUS | Job 5a5a2927-4e72-4513-bb3f-bfa38d559393 failed with LLR-004 at post_diagnostic. | AMBIGUOUS → RESOLVED after failing Pass2 payload is captured and subtype classified. | 2026-04-27 | Add LLR-004 subtype classification: MODEL_OUTPUT_INVALID vs RULE_TOO_STRICT vs REGISTRY_DRIFT.
RCA-DIALOGUE-GATE-001 | QG_DIALOGUE_ATTRIBUTION_UNDERAUDITED | Pass4 / Quality Gate | quality_gate / pass4 | False or over-broad dialogue attribution failures on reachable jobs. | Gate used insufficiently diagnostic mechanism detection; valid dialogue analysis could be under-recognized without attribution/rendering vocabulary. | GATE_LOGIC | MEDIUM | ENFORCEMENT | Previously blocked completed reports; now resolved at gate-level but upstream reachability can obscure proof. | Keep diagnostic-grounded dialogue gate: marker OR mechanism-language path; preserve fail-closed behavior and regression tests. | lib/evaluation/pipeline/qualityGate.ts; lib/evaluation/pipeline/gates.ts; lib/evaluation/pipeline/runPass3Synthesis.ts; lib/evaluation/pipeline/runPipeline.ts | E2E-06 quality_gate; E2E-07 pass4_cross_check | __tests__/lib/evaluation/pipeline/qualityGate.coverage.test.ts; scripts/pipeline/gate-replay-check.ts; scripts/pipeline/run-dominatus-i4-eval.ts | RESOLVED | PR #245; post-fix reachable runs did not re-trigger QG_DIALOGUE_ATTRIBUTION_UNDERAUDITED. | Upstream PASS1/LLR reachability for additional live samples. | 2026-04-27 | Preserve tests; only reopen if fresh post-fix job triggers same gate with diagnostic evidence.
RCA-ATOMIC-PERSISTENCE-001 | ATOMIC_PERSISTENCE | Persistence / Supabase RPC | persist_artifacts + finalize | Artifact/job completion could split or DB RPC could fail with ambiguity. | SQL ambiguity in atomic persistence RPC plus prior sequential write risk. | DB_RPC | LOW | ENFORCEMENT | Could create completion/artifact mismatch or failed success path. | Use atomic RPC for V2 persistence and source-align #variable_conflict/use_column hotfix. | lib/evaluation/persistEvaluationResultV2.ts; lib/evaluation/artifactPersistence.ts; supabase/migrations/*persist_evaluation_v2_atomic* | E2E-08 persist_artifacts + finalize; E2E-10 proof harness | __tests__/lib/evaluation/persistEvaluationResultV2.boundary-gate.test.ts; scripts/jobs-supabase-contract-smoke.mjs; scripts/jobs-smoke-service-role.mjs; npm run soak:qualify | RESOLVED | PR #241/#242/#243; job 29089ed6 complete; artifact af699bd8 exists; 100k soak proof. | None unless regression appears. | 2026-04-27 | Keep migration/source aligned and include atomic proof in release guard.
RCA-FAILURE-ENVELOPE-001 | PIPELINE_FAILURE_ENVELOPE | Failure Diagnostics | pipeline failure handling | Current QG failure path now emits structured envelope, but diagnostic payload is not yet proven across all failure classes. | Envelope enforcement exists on current path; full diagnostic topology still requires fresh non-null pipeline_failure_diagnostics samples. | OBSERVABILITY | MEDIUM | ENFORCEMENT | Without consistent envelope/diagnostics, failures become harder to classify into RCCA rows. | Keep envelope required; run targeted post-fix diagnostic failures to capture non-null diagnostics and classify by stage. | lib/evaluation/processor.ts; lib/evaluation/pipeline/failures.ts; lib/evaluation/processor/finalizeJobFailure.ts | E2E-03 claim → pipeline_run; E2E-06 quality_gate; E2E-10 proof harness | tests/evaluation/pipeline/pipeline-e2e.test.ts; __tests__/lib/evaluation/processor.test.ts; scripts/e2e-golden-run.sh | PARTIAL | Recent QG failure job 40b377de had pipeline_failure_envelope; older jobs lacked envelope as pre-fix baseline. | Need fresh non-null diagnostics sample. | 2026-04-27 | Generate targeted post-fix failure proof and store RCA subtype in ledger.
RCA-U2-001 | U2_SCORE_CONFIDENCE_MISMATCH | Quality Gate | quality_gate | Score >= 6 while criterion confidence is low. | No hard binding between derived confidence and score authority. | SYSTEM | HIGH | ENFORCEMENT | Allows over-claiming evaluation authority and lets weak evidence look stronger than it is. | Enforce QG_FIDELITY_SCORE_CONFIDENCE_MISMATCH; fail/hold or cap authority when low-confidence score exceeds allowed ceiling. | lib/evaluation/pipeline/qualityGate.ts | E2E-06 quality_gate; E2E-10 proof harness | __tests__/lib/evaluation/pipeline/qualityGate.coverage.test.ts; tests/evaluation/pipeline/pipeline-e2e.test.ts; scripts/e2e-golden-run.sh | NOT_STARTED | U2 Batch 2 seed from 2026-04-27 workbook discussion; must close after confidence derivation exists. | Blocked by confidence derivation RCA. | 2026-04-27 | Implement after RCA-U2-003 so confidence source is deterministic. | RCA-U2-003
RCA-U2-002 | U2_SUMMARY_WASHING | Pass3 / Synthesis | pass3_synthesis | Summary presents positive/clean authority while low-scoring or weak criteria exist. | Synthesis layer can smooth contradictions and omit lowest-scoring weakness cluster. | SYSTEM | HIGH | ENFORCEMENT | Narrative distortion: user-facing summary can sound better than the score/evidence profile supports. | Require Pass3 summary to reference at least one weakest/lowest-scoring criteria cluster; gate QG_SUMMARY_OMITS_WEAKNESS if omitted. | lib/evaluation/pipeline/runPass3Synthesis.ts; lib/evaluation/pipeline/qualityGate.ts | E2E-05 pass3; E2E-06 quality_gate; E2E-10 proof harness | __tests__/lib/evaluation/pipeline/pass3-semantic-contract.test.ts; __tests__/lib/evaluation/pipeline/qualityGate.coverage.test.ts; PV115 golden fixture | NOT_STARTED | U2 Batch 2 seed; anti-washing must be separate from score-confidence mismatch. | Blocked by anchor enforcement so weakness reference has concrete textual grounding. | 2026-04-27 | Implement after RCA-U2-006 anchor requirement is defined. | RCA-U2-006
RCA-U2-003 | U2_CONFIDENCE_DERIVATION | Pipeline / Confidence | synthesisToEvaluationResultV2 | Confidence inconsistent with evidence profile or still treated as model-emitted/static metadata. | Confidence is not deterministically derived from criterion evidence/count/quality topology. | SYSTEM | HIGH | ENFORCEMENT | Invalid authority signal can propagate into score, summary, persistence, and UI. | Derive confidence from evidence profile and deterministic reason codes; populate governance.confidence_label and confidence_reasons. | lib/evaluation/pipeline/runPipeline.ts; lib/evaluation/schemas/evaluation-result-v2.ts; lib/evaluation/pipeline/propagationIntegrity.ts | E2E-05 pass3; E2E-06 quality_gate; E2E-10 proof harness | tests/evaluation/pipeline/pipeline-e2e.test.ts; __tests__/lib/evaluation/processor.real-gate.test.ts; PV115 golden fixture | PARTIAL | Remote branch feat/u2-propagation-enforcement includes U2 commit 8ecdde70; deterministic confidence implementation pushed; focused local tests green. ROADMAP.md updated by ca12ade4 to PARTIAL REMOTE IMPLEMENTATION / LIVE_PROOF_PENDING. Live server/API artifact proof still pending. | LIVE_PROOF_PENDING | 2026-04-28 | Run live U2 closure proof and capture governance.confidence_label, confidence_reasons, propagation_summary, and progress.gate_enforcement before RESOLVED. | NONE
RCA-U2-004 | U2_PROPAGATION_MISSING | Pipeline / Gate | synthesis + quality_gate | Weak criterion signals do not affect report-level authority. | No aggregation/profiling layer converts per-criterion confidence/evidence into upstreamIntegrity. | SYSTEM | HIGH | ENFORCEMENT | Report-level dishonesty: weak evidence can still produce high-authority artifact presentation. | Compute propagation profile: low/moderate/scorable-low/missing/weak evidence counts plus upstreamIntegrity strong¦mixed¦weak. | lib/evaluation/pipeline/qualityGate.ts; lib/evaluation/pipeline/runPipeline.ts; lib/evaluation/schemas/evaluation-result-v2.ts | E2E-06 quality_gate; E2E-08 persist_artifacts + finalize; E2E-10 proof harness | __tests__/lib/evaluation/pipeline/qualityGate.coverage.test.ts; __tests__/lib/evaluation/persistEvaluationResultV2.boundary-gate.test.ts; scripts/e2e-golden-run.sh | NOT_STARTED | U2 Batch 2 seed; creates report-level propagation authority. | Blocked by confidence derivation; cannot aggregate unstable confidence source. | 2026-04-27 | Implement after RCA-U2-003. | RCA-U2-003
RCA-U2-005 | U2_UI_AUTHORITY_MISMATCH | UI / Classification | report_render | High-confidence UI/banner can appear on weak or low-confidence artifact. | UI classification is not bound to confidence topology and propagation integrity. | SYSTEM | HIGH | ENFORCEMENT | User-facing false authority even if backend has warnings or mixed/weak confidence. | Update warningClassification so high-confidence banner requires PASS + non-low confidence + no severe propagation/fidelity warning. | lib/evaluation/warningClassification.ts; components/report/*; app/evaluate/[jobId]/page.tsx | E2E-09 report_render; E2E-10 proof harness | __tests__/lib/evaluation/warningClassification.test.ts; scripts/check-e2e-summary.mjs; PV115 golden fixture | NOT_STARTED | U2 Batch 2 seed; close after propagation layer exists. | Blocked by propagation profile; UI needs stable upstreamIntegrity input. | 2026-04-27 | Implement after RCA-U2-004. | RCA-U2-004
RCA-U2-006 | U2_EVIDENCE_ANCHOR_ENFORCEMENT | Quality Gate / Pass2 | pass2 + quality_gate | Criterion rationale lacks textual anchors such as quote, scene, action, or concrete manuscript reference. | No enforced citation/anchor requirement for rationale validity; scope is anchor enforcement only, not full confidence derivation. | MODEL + SYSTEM | MEDIUM | ENFORCEMENT | Shallow reasoning can appear valid and later be polished by synthesis. | Require at least one concrete textual anchor for scorable rationale OR downgrade confidence / trigger hold threshold. | lib/evaluation/pipeline/qualityGate.ts; lib/evaluation/pipeline/runPass2.ts; lib/evaluation/pipeline/prompts/pass2-editorial.ts; lib/evaluation/pipeline/__tests__/runPass2.anchor-enforcement.test.ts | E2E-04 pass1 + pass2; E2E-06 quality_gate; E2E-10 proof harness | __tests__/lib/evaluation/pipeline/qualityGate.coverage.test.ts; lib/evaluation/pipeline/__tests__/runPass2.anchor-enforcement.test.ts; __tests__/lib/evaluation/processor.real-gate.test.ts; PV115 golden fixture | PARTIAL | Remote branch feat/u2-propagation-enforcement includes U2 commit 8ecdde70 with runPass2 anchor enforcement and runPass2.anchor-enforcement.test.ts; focused local tests green. Live server/API artifact proof still pending. | LIVE_PROOF_PENDING | 2026-04-28 | Run live/real-path proof and capture reason_codes / NO_TEXTUAL_ANCHOR evidence when applicable before RESOLVED. | NONE
RCA-BOUNDARY-SHAPE-001 | BOUNDARY_VALIDATION_SHAPE_GAP | Persistence Boundary | persistEvaluationResultV2 / validation | RESOLVED: raw persisted PASS artifact path was verified; gate_enforcement is stored at progress.gate_enforcement and PASS-path regression exists. | No defect found. Ambiguity came from an unproven raw-vs-normalized proof gap. Structural validation runs on raw EvaluationResultV2 before persistence; pipeline artifact validation runs on an intentional projection; raw EvaluationResultV2 is persisted. | PROOF_GAP_CLOSED | MEDIUM | CALIBRATION_CONFIRMED | Removes false uncertainty around boundary validation; restores confidence that Step 1.5 structural validation is enforced on the covered PASS path. | No code change required from this check. Preserve PASS-path regression asserting progress.gate_enforcement is populated; continue querying progress->'gate_enforcement' rather than expecting a standalone column. | lib/evaluation/persistEvaluationResultV2.ts; lib/evaluation/pipeline/validateEvaluationArtifact.ts; lib/evaluation/schemas/evaluation-result-v2.ts; lib/evaluation/artifactPersistence.ts | E2E-08 persist_artifacts + finalize; E2E-10 proof harness | scripts/e2e-golden-run.sh; scripts/check-e2e-summary.mjs; __tests__/lib/evaluation/persistEvaluationResultV2.boundary-gate.test.ts | RESOLVED | RESOLVED with code-level + live production-data proof. Live SQL against latest complete job 533a77a5-11cd-4b06-9167-41332cd12390 returned progress->'gate_enforcement' populated (not null): validation_result='PASS', gate_decision='PASS', gate_reason='Artifact validation result is PASS', validated_at='2026-04-27T04:26:09.435Z', confidence={confidence:'high', reasons:[]}, reason_codes=[]. artifact_schema=evaluation_result_v2; completed_at=2026-04-27T04:26:09.436+00:00. Code proof: validateStructuralArtifact runs on raw EvaluationResultV2 before buildArtifactForValidation projection; raw artifact is persisted via p_artifact_content/p_evaluation_result; PASS-path regression passes 6/6. | None. Closed before U2 code lands. | 2026-04-27 | Closed. Use progress->'gate_enforcement' for future DB checks; do not query a nonexistent top-level gate_enforcement column. | NONE

## E2E_SCRIPT_MAP
Stage ID | E2E Stage | What It Tells You | Canonical / Likely Relevant Files | Proof / Regression Scripts | RCA Link Use | Notes
E2E-01 | job creation → kickoff | Queue/scheduling overhead | app/api/jobs/route.ts; app/api/evaluate/route.ts; app/api/internal/jobs/route.ts; lib/jobs/triggerWorker.ts; lib/jobs/store.ts; lib/jobs/jobStore.supabase.ts | scripts/jobs-smoke-real.mjs; scripts/jobs-smoke-service-role.mjs; scripts/jobs-supabase-contract-smoke.mjs | Use for queued/triggered/stuck-before-claim RCA rows | Include auth, private-beta, service-role, and kickoff URL failures.
E2E-02 | kickoff → claim | Worker availability lag | app/api/workers/process-evaluations/route.ts; lib/jobs/jobStore.supabase.ts; supabase/migrations/*claim*; supabase/migrations/*evaluation_jobs* | scripts/jobs-test-contention.mjs; scripts/jobs-lease-contention-test.mjs; scripts/jobs-validate-invariants.mjs | Use for claim/lease/heartbeat/worker_id RCA rows | Known prior classes: active_claim_invalid, blocked_triggered, claim RPC schema drift.
E2E-03 | claim → pipeline_run start | Fetch manuscript cost | lib/evaluation/processor.ts; lib/jobs/phase1.ts; lib/jobs/phase2.ts; lib/config/evaluationRuntimeConfig.ts; lib/config/config.ts | __tests__/lib/evaluation/processor.test.ts; __tests__/lib/evaluation/processor.atomic-claim.test.ts | Use for manuscript fetch, phase start, config, timeout RCA rows | Separate manuscript fetch from LLM execution.
E2E-04 | pass1 + pass2 (parallel) | OpenAI parallel call cost and upstream output stability | lib/evaluation/pipeline/runPass1.ts; lib/evaluation/pipeline/runPass2.ts; lib/evaluation/pipeline/prompts/pass1-craft.ts; lib/evaluation/pipeline/prompts/pass2-editorial.ts; lib/evaluation/pipeline/runPipeline.ts; lib/llm/jsonParseBoundary.ts | __tests__/lib/evaluation/processor.canonical-pipeline.test.ts; tests/evaluation/pipeline/pipeline-e2e.test.ts; scripts/pipeline/run-phase2-7-real-run.ts | Use for PASS1_FAILED, PASS2, JSON, LLR, prompt/token RCA rows | Primary current blocker: PASS1 output feasibility, finish_reason=length.
E2E-05 | pass3 | Synthesis cost, reconciliation, anti-washing behavior | lib/evaluation/pipeline/runPass3Synthesis.ts; lib/evaluation/pipeline/prompts/pass3-synthesis.ts; lib/evaluation/pipeline/pass3ContractValidator.ts; lib/evaluation/pipeline/normalization.ts | __tests__/lib/evaluation/pipeline/pass3-semantic-contract.test.ts; __tests__/lib/evaluation/pipeline/pass3-backfill-quality.test.ts; __tests__/lib/evaluation/pipeline/pass3.test.ts | Use for U2 propagation, synthesis smoothing, score-summary mismatch RCA rows | Next phase: U2 propagation enforcement and Pass3 weakness-reference constraint.
E2E-06 | quality_gate | Gate overhead and deterministic acceptance/rejection | lib/evaluation/pipeline/qualityGate.ts; lib/evaluation/pipeline/gates.ts; lib/evaluation/pipeline/validateEvaluationArtifact.ts; lib/evaluation/pipeline/persistArtifactValidation.ts | __tests__/lib/evaluation/pipeline/qualityGate.coverage.test.ts; scripts/pipeline/gate-replay-check.ts; scripts/pipeline/gate-replay-check.ts --fail-on-any | Use for QG_* RCA rows and fidelity gate rows | Gate failures must carry structured envelope + diagnostics when applicable.
E2E-07 | pass4_cross_check | Perplexity call and retry cost | lib/evaluation/pipeline/perplexityCrossCheck.ts; lib/evaluation/governance/evaluatePass4Governance.ts; lib/governance/canonRegistry.ts; lib/governance/injectionMap.ts | scripts/pipeline/run-dominatus-i4-eval.ts; scripts/eval-chapter10b.ts | Use for cross-check/provider/governance RCA rows | Provider-compatible prompt doctrine applies here.
E2E-08 | persist_artifacts + finalize | DB write overhead and artifact/job atomicity | lib/evaluation/persistEvaluationResultV2.ts; lib/evaluation/artifactPersistence.ts; schemas/evaluation-result-v2.ts; lib/evaluation/schemas/evaluation-result-v2.ts; supabase/migrations/* | __tests__/lib/evaluation/persistEvaluationResultV2.boundary-gate.test.ts; scripts/jobs-supabase-contract-smoke.mjs; scripts/jobs-smoke-service-role.mjs | Use for persistence/finalize/artifact shape/RPC RCA rows | Block B now enforced; include PR #241/#242/#243 references in RCA rows.
E2E-09 | report rendering | Final user-visible authority and warning classification | app/evaluate/[jobId]/page.tsx; app/evaluation/[jobId]/page.tsx; app/jobs/[jobId]/page.tsx; components/evaluation/*; components/report/*; warningClassification.ts | warningClassification.test.ts; processor.real-gate.test.ts | Use for UI authority/high-confidence contradiction RCA rows | Tie to U2: PASS + low confidence must not render high-authority UI.
E2E-10 | proof harness / soak | End-to-end regression, reliability, and invariant proof | scripts/e2e-golden-run.sh; scripts/check-e2e-summary.mjs; scripts/soak/run-soak.ts; scripts/gate-reliability.sh; docs/operations/evidence/runs/* | npm run soak:qualify; scripts/e2e-golden-run.sh; scripts/check-e2e-summary.mjs | Use for reliability-gate, proof-pack, 100k soak RCA rows | 100k soak passed with zero lost writes/wrong-location edits/unclassified failures.

## RCA_SCRIPT_LINKS
RCA_ID | E2E Stage ID | Relevance | Known Failing / Known Proof Surface | Investigation Files / Scripts
RCA-PASS1-TOKEN-001 | E2E-04 | PRIMARY | Known failing | runPass1.ts; pass1-craft.ts; runPipeline.ts; jsonParseBoundary.ts; scripts/pipeline/run-phase2-7-real-run.ts
RCA-PASS1-TOKEN-001 | E2E-10 | SECONDARY | Proof harness | scripts/e2e-golden-run.sh; scripts/check-e2e-summary.mjs; scripts/jobs-smoke-service-role.mjs
RCA-LLR-004-001 | E2E-04 | PRIMARY | Known failing / ambiguous cause | runPass2.ts; pass2-editorial.ts; ACTIVE_RULES.ts; canonRegistry.ts; scripts/pipeline/run-phase2-7-real-run.ts
RCA-LLR-004-001 | E2E-06 | SECONDARY | Rule/gate calibration context | qualityGate.ts; lessonsLearned/*; qualityGate.coverage.test.ts
RCA-DIALOGUE-GATE-001 | E2E-06 | PRIMARY | Known resolved/proof surface | qualityGate.ts; gates.ts; qualityGate.coverage.test.ts; gate-replay-check.ts
RCA-DIALOGUE-GATE-001 | E2E-07 | SECONDARY | Cross-check context | evaluatePass4Governance.ts; perplexityCrossCheck.ts
RCA-ATOMIC-PERSISTENCE-001 | E2E-08 | PRIMARY | Known resolved/proof surface | persistEvaluationResultV2.ts; artifactPersistence.ts; persist_evaluation_v2_atomic migrations; persistEvaluationResultV2.boundary-gate.test.ts
RCA-ATOMIC-PERSISTENCE-001 | E2E-10 | SECONDARY | Reliability proof | soak:qualify; gate-reliability.sh; jobs-smoke-service-role.mjs
RCA-FAILURE-ENVELOPE-001 | E2E-03 | PRIMARY | Partial diagnostic proof | processor.ts; finalizeJobFailure.ts; failures.ts; processor.test.ts
RCA-FAILURE-ENVELOPE-001 | E2E-06 | SECONDARY | Gate failure envelope proof | qualityGate.ts; qualityGate.coverage.test.ts; pipeline-e2e.test.ts
RCA-U2-001 | E2E-06 | PRIMARY | New U2 gate failure class | qualityGate.ts; qualityGate.coverage.test.ts; QG_FIDELITY_SCORE_CONFIDENCE_MISMATCH
RCA-U2-001 | E2E-10 | SECONDARY | Proof harness | scripts/e2e-golden-run.sh; PV115 golden fixture
RCA-U2-002 | E2E-05 | PRIMARY | Pass3 anti-washing proof | runPass3Synthesis.ts; pass3-semantic-contract.test.ts; QG_SUMMARY_OMITS_WEAKNESS
RCA-U2-002 | E2E-06 | SECONDARY | Gate catches summary omission | qualityGate.ts; qualityGate.coverage.test.ts
RCA-U2-003 | E2E-05 | PRIMARY | Derived confidence source | runPipeline.ts; synthesisToEvaluationResultV2; evaluation-result-v2.ts
RCA-U2-004 | E2E-06 | PRIMARY | Propagation integrity profile | qualityGate.ts; runPipeline.ts; upstreamIntegrity strong¦mixed¦weak
RCA-U2-004 | E2E-08 | SECONDARY | Persistence needs propagation trace | persistEvaluationResultV2.boundary-gate.test.ts
RCA-U2-005 | E2E-09 | PRIMARY | Report authority rendering | warningClassification.ts; warningClassification.test.ts; components/report/*
RCA-U2-006 | E2E-04 | PRIMARY | Pass2 rationale anchor source | runPass2.ts; pass2-editorial.ts; anchor detector / textual reference
RCA-U2-006 | E2E-06 | SECONDARY | Gate downgrades/holds on missing anchors | qualityGate.ts; qualityGate.coverage.test.ts
RCA-BOUNDARY-SHAPE-001 | E2E-08 | PRIMARY | Resolved proof surface | persistEvaluationResultV2.ts; validateStructuralArtifact raw check; evaluation-result-v2.ts; persistEvaluationResultV2.boundary-gate.test.ts (6/6 passing)
RCA-BOUNDARY-SHAPE-001 | E2E-10 | SECONDARY | Resolved / ongoing guard | scripts/e2e-golden-run.sh; scripts/check-e2e-summary.mjs; live SQL must query progress->'gate_enforcement'
PV115-GOLDEN-FIXTURE | E2E-10 | VERIFICATION | Proof fixture after U2 closures | PV115 golden fixture test; scripts/e2e-golden-run.sh; scripts/check-e2e-summary.mjs

## RCA_BATCH_PLAN
Batch | Target Count | Theme | Seed / Candidate RCAs | Why This Batch | Status
Batch 1 | 5 | Current high-signal failures and resolved infra | PASS1 token, LLR-004, Dialogue gate, Atomic persistence, Failure envelope diagnostics | Establishes RCA system of record; separates open blockers, resolved proofs, and partial diagnostic evidence | APPLIED
Batch 2 | 6 | U2 / fidelity enforcement | RCA-U2-001..006: score-confidence mismatch, summary washing, derived confidence, propagation missing, UI authority mismatch, evidence anchor enforcement | Turns U2 into six closeable failure classes with dependencies: 001→003, 005→004, 002→006 | APPLIED / READY FOR EXECUTION
Batch 3 | 5–10 | Pass1 output feasibility variants | Prompt bloat, schema bloat, manuscript payload edge, JSON truncation, retry/fail-closed diagnostics | Current upstream blocker to reach gates consistently | PENDING
Batch 4 | 5–10 | LLR and governance calibration | LLR-004 variants, post-structural vs post-diagnostic, canonical term drift, provider output normalization | Separates valid enforcement from overblocking | PENDING
Batch 5 | 5–10 | UI/report truth surface | High-confidence banner mismatch, report not ready states, warning classification, report rendering authority | Ensures user-visible output matches governance truth | PENDING
Final patch | Boundary + PV115 | APPLIED | Added RCA-BOUNDARY-SHAPE-001 and VERIFICATION_ARTIFACTS/PV115; execution block patched | Prevents pseudo-RCA drift and boundary overclaiming | 2026-04-27
Final micro-patch | PV115 + ambiguity lifecycle | APPLIED | Added VERIFICATION_ARTIFACTS.PROMOTION_RULE; normalized RCA-LLR-004-001 and RCA-BOUNDARY-SHAPE-001 lifecycle to AMBIGUOUS → RESOLVED. | Keeps proof artifacts promotion-gated and ambiguity classification consistent before U2 execution. | 2026-04-27
Boundary closure | 1 | Raw PASS shape proof | RCA-BOUNDARY-SHAPE-001 RESOLVED with live SQL evidence: job 533a77a5-11cd-4b06-9167-41332cd12390, progress.gate_enforcement populated, artifact_schema=evaluation_result_v2, completed_at=2026-04-27T04:26:09.436+00:00. | Closed calibration uncertainty before U2 code lands; confirmed live DB path plus raw validator order, raw persistence, and PASS-path regression. | RESOLVED 2026-04-27
U2 remote implementation checkpoint | 2 | RCA-U2-003 / RCA-U2-006 partial remote status | Commit 8ecdde70 pushed: deterministic confidence + anchor enforcement; ROADMAP.md correction ca12ade4 records PARTIAL REMOTE IMPLEMENTATION / LIVE_PROOF_PENDING. | Converts local truth into repo truth while preserving doctrine that live proof is still required before RESOLVED. | PARTIAL REMOTE / APPLIED 2026-04-28

## ENFORCEMENT_SCALE
Value | Definition | Use In Workbook | Allowed Status?
ENFORCED | Hard gate or runtime invariant is implemented, tested, and has proof evidence. | CURRENT_STATE, ROADMAP_LANES, RCA, U_GATES_ENFORCEMENT | YES
ENFORCED — boundary scope | Hard gate is true only for the named boundary/scope; not a whole-system claim. | CURRENT_STATE, Complete-Partially-Pending | YES
PARTIAL | Implemented or specified in part, but not fully proven or not end-to-end authoritative. | All tracker sheets | YES
OBSERVED | Detected or measured, but not yet enforced as a gate/control-flow rule. | RCA, CURRENT_STATE | YES
OPEN | Known issue/failure class requiring root-cause closure. | RCA, Current State | YES
RESOLVED | Root cause fixed and proof evidence exists. | RCA | YES
NOT_STARTED | Specified or known work that has not been implemented. | ROADMAP_LANES, EXECUTION_BLOCK | YES
BLOCKED | Cannot progress until listed dependency/RCA is addressed. | ROADMAP_LANES, RCA_BATCH_PLAN | YES
AMBIGUOUS | Cause cannot be assigned yet; requires classification before fix can be treated as final. | RCA | YES

## RCA_LINK_MAP
RCA_ID | Linked_Sheet | Linked_Key_or_Row | Relationship | Update_Instruction
RCA-PASS1-TOKEN-001 | CURRENT_STATE | PASS1_OUTPUT_FEASIBILITY | Primary open blocker | Show as OPEN / blocking gate reachability.
RCA-PASS1-TOKEN-001 | ROADMAP_LANES | Pipeline Feasibility | Lane blocker | Do not treat as latency-only; this is feasibility/fidelity reachability.
RCA-PASS1-TOKEN-001 | Complete-Partially-Pending | Pass1 output feasibility | Pending/partial | Use minimal unblocking patch before large latency work.
RCA-LLR-004-001 | CURRENT_STATE | LLR_POST_STRUCTURAL_BLOCK / LLR-004 | Primary open blocker | Keep AMBIGUOUS until failing Pass2 output is inspected.
RCA-LLR-004-001 | ROADMAP_LANES | Governance / Pipeline Feasibility | Calibration blocker | Separate model invalidity from rule strictness and registry drift.
RCA-DIALOGUE-GATE-001 | CURRENT_STATE | Dialogue Gate V2 | Resolved gate-level proof | Keep closed unless fresh post-fix evidence reopens.
RCA-DIALOGUE-GATE-001 | Complete-Partially-Pending | Dialogue Gate V2 | Completed with caveat | Caveat: upstream reachability can mask further proof.
RCA-ATOMIC-PERSISTENCE-001 | CURRENT_STATE | Atomic persistence RPC | Resolved proof row | Keep as release guard / proof evidence.
RCA-ATOMIC-PERSISTENCE-001 | Complete-Partially-Pending | Atomicity / production proof | Completed | No action unless regression appears.
RCA-FAILURE-ENVELOPE-001 | CURRENT_STATE | Failure Diagnostics | Partial/open diagnostic proof | Need fresh non-null diagnostics sample.
RCA-U2-001 | CURRENT_STATE | U2_PROPAGATION / U2_SCORE_CONFIDENCE_MISMATCH | Primary U2 failure class | Show as NOT_STARTED; blocked by RCA-U2-003 until confidence derivation exists.
RCA-U2-001 | EXECUTION_BLOCK | STEP 3 | Execution sequencing | Close after RCA-U2-003 and RCA-U2-004 inputs are stable enough for gate check.
RCA-U2-002 | EXECUTION_BLOCK | STEP 5 / PASS3_SYNTHESIS | Execution sequencing | Anti-washing closes after RCA-U2-006 anchor enforcement is defined.
RCA-U2-003 | CURRENT_STATE | CONFIDENCE_SYSTEM | Primary U2 prerequisite | First U2 closure item; all downstream U2 authority depends on it.
RCA-U2-003 | EXECUTION_BLOCK | STEP 1 | Execution sequencing | Start U2 implementation here.
RCA-U2-004 | EXECUTION_BLOCK | STEP 2 / U2_PROPAGATION | Execution sequencing | Close after RCA-U2-003; supplies upstreamIntegrity for gate/UI.
RCA-U2-004 | ROADMAP_LANES | Governance / Artifact Quality / Confidence | Lane blocker | Replace prose U2 blocker with this RCA dependency.
RCA-U2-005 | ROADMAP_LANES | User UI / UI_AUTHORITY | Lane blocker | Close after RCA-U2-004; UI authority must read propagation topology.
RCA-U2-005 | EXECUTION_BLOCK | STEP 6 | Execution sequencing | Final UI authority lock after backend propagation exists.
RCA-U2-006 | CURRENT_STATE | EVIDENCE_VALIDATION | Primary U2 failure class | Anchor/citation enforcement only; do not merge with confidence derivation or score mismatch.
RCA-U2-006 | EXECUTION_BLOCK | STEP 4 | Execution sequencing | Close before RCA-U2-002 so anti-washing references concrete evidence.
RCA-BOUNDARY-SHAPE-001 | CURRENT_STATE | BOUNDARY_VALIDATION / BOUNDARY_VALIDATION_SHAPE_GAP | Resolved validation-risk row | Boundary validation can now show ENFORCED without calibration uncertainty; keep PASS-path regression as guard.
RCA-BOUNDARY-SHAPE-001 | ROADMAP_LANES | Persistence / Boundary | Resolved lane proof | Persistence / Boundary lane may state boundary raw-shape gap RESOLVED; future schema changes require re-proof.
RCA-BOUNDARY-SHAPE-001 | EXECUTION_BLOCK | PARALLEL_VALIDATION_TRACK | Closed parallel proof track | No longer blocks cockpit honesty; U2 execution may proceed with boundary risk closed.
PV115-GOLDEN-FIXTURE | VERIFICATION_ARTIFACTS | PV115-GOLDEN-FIXTURE | Verification artifact, not RCA | Requires U2 RCAs closed before it can mark U2 proof-ready.
PV115-GOLDEN-FIXTURE | EXECUTION_BLOCK | STEP 7 | Proof step | Keep as verification artifact and do not count as RCA-U2-007.
RCA-U2-003 | Complete-Partially-Pending | RCA-U2-003 derived confidence | Partial/local proof view | Keep PARTIAL until committed remote branch and live server/API artifact proof exist.
RCA-U2-006 | Complete-Partially-Pending | RCA-U2-006 evidence anchor enforcement | Partial/local proof view | Keep PARTIAL until NO_TEXTUAL_ANCHOR changes are pushed and live proof exists.
RCA-U2-003 | SOURCE_INDEX | Local-vs-remote U2 verification | Evidence source | Do not use Phase 2E/RLS logs to close U2.
RCA-U2-006 | SOURCE_INDEX | Local-vs-remote U2 verification | Evidence source | Do not use Phase 2E/RLS logs to close U2.

## VERIFICATION_ARTIFACTS
ARTIFACT_ID | TYPE | PURPOSE | DEPENDS_ON_RCA | STATUS | RULE | NOTE | LAST_UPDATED | PROMOTION_RULE
PV115-GOLDEN-FIXTURE | REGRESSION / PROOF FIXTURE | Validate U2 fidelity enforcement across real PV115 signals and ensure confidence cannot stay high when required signals are missed. | RCA-U2-001; RCA-U2-002; RCA-U2-004; RCA-U2-005; RCA-U2-006 | NOT_READY | Must pass before U2 is marked ENFORCED. | Not an RCA — verification-only artifact. | 2026-04-27 | Must pass before U2_FIDELITY_ENFORCEMENT can be marked ENFORCED.
ARTIFACT_ID | EVIDENCE_SIGNALS | FAILS_IF | CODE_SURFACE | SCRIPT_SURFACE | CURRENT_BLOCKER | NEXT_ACTION | OWNER_NOTES | PROMOTION_RULE
PV115-GOLDEN-FIXTURE | dogs / Mexico parallel / meta-fiction / river force imagery / deliberate withholding | Artifact misses signals while summary/confidence remains high-authority or anti-washing does not fire. | qualityGate.ts; runPipeline.ts; runPass3Synthesis.ts; warningClassification.ts; evaluation-result-v2.ts | scripts/e2e-golden-run.sh; scripts/check-e2e-summary.mjs; PV115 golden fixture test | Waiting on U2 RCA closures. | Implement fixture after U2 RCA gate surfaces exist. | Fixture, not failure class. | Required green before U2_FIDELITY_ENFORCEMENT moves to ENFORCED.